## Sheet1
Phases |  | Phases |  |  |  |  | Contract |  | Development
[7 empty] | Implementation |  | Post Go-Live Support
[7 empty] | Go-Live |  | Vacations
PRODUCTION RELEASE = <P>
| 2015 | [11 empty] | 2016 | 2016
| June |  | July |  | August |  | September |  | October |  | November | December | January | January | February | March | April | May | June | July | August | September | October | November | December
Prudential |  |  |  | SSO | Site config |  | 9/1 (UAT) | Early Adopters | Early Adopters | ALL Users
[5 empty] | SSO (SP setup) |  | SSO (Reg flow) |  |  |  | Skills Mgr Endorsement?
Janssen |  |  |  |  | Site config & scale |  |  | Config | UAT | TBD
C&J Energy | [10 empty] | TBD
Gymboree
Sysco Renewal + Mgr
AARP
Farmers
Texas A&M
Monsanto
Go-Live
Production Updates | [7 empty] | <P> Sept 19 | TBD
Migrate to AWS | [5 empty] | Code Rep.Update |  |  |  | platform upgrades | Proof of Concept | TBD | Internap expires
VACATIONS
Laurel | [5 empty] | Aug 9-23
Amy | [5 empty] | Aug 17-21
Chris |  |  |  |  | Aug 3-17
Scott |  |  |  |  | July 30 - Aug 9
Stephen
Casey |  |  |  |  | aug 10-14